Charter Summary

| Field | Value |
| --- | --- |
| Project name | Automated Production Reporting (Pilot Line) |
| Sponsor | Operations Sponsor |
| Project manager | Internal Project Manager |
| Business problem | Manual reporting delay up to 24 hours |
| Objectives | Latency < 60 seconds, uptime ≥ 99.9%, KPI totals match shift logs |
| Scope | Single production line pilot, planned cutover window |
| Approval date | Oct 1, 2025 |

Project Phases and Dates

| Phase | Date range | Key output |
| --- | --- | --- |
| Phase 1: Requirements and KPI Definition | Oct 1, 2025 to Oct 7, 2025 | KPI list, acceptance criteria, scope sign-off |
| Phase 2: Data Mapping and Security Design | Oct 8, 2025 to Oct 21, 2025 | Data dictionary draft, SQL schema, security approach |
| Phase 3: Development | Oct 22, 2025 to Nov 13, 2025 | Python middleware, SQL writes, service setup |
| Phase 4: Testing and UAT | Nov 14, 2025 to Nov 28, 2025 | Recovery, accuracy, load tests, UAT results |
| Phase 5: Pilot and Handover | Dec 1, 2025 to Dec 12, 2025 | Pilot monitoring, closeout, and handoff are complete |

Top Risks

| ID | Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- | --- |
| R1 | OT, IT access delays | Med | High | Early firewall allowlist request, pre-approval review |
| R2 | Developer time constraints | High | High | 60-hour time block commitment approval |
| R3 | KPI definition drift | Med | High | KPI glossary and data dictionary, QA validation in UAT |